# Essential scoping questions for Subject Matter Expert (SME) discussion

# Project fundamentals and strategic alignment

## 1. Project purpose and context

- Tell me in as much detail as possible what the aim of this project is (purpose and audience). How was the need for it identified?

- What is the return on investment expectation for this project?

- How does this project align with the University of Southampton's Education Strategy, Student Experience Strategy, or Triple Helix framework?

- Is this project supporting the education of UoS students (non-chargeable) or external stakeholders (chargeable)?

## 2. Stakeholder management and governance

- Who will have the final sign-off for the project?

- How many other partners will be involved in the project?

- Can key decision-makers be included in conversations about the project early on?

- What internal review processes are required for clinical accuracy and content validation?

- What will be your success metrics for both staff and student benefits?

# Learning objectives and pedagogical design

## 3. Learning outcomes specification

- How many discrete learning objectives need to be covered?

- What are you aiming to achieve through this eLearning? (Use Bloom's taxonomy)

- By the end of this module/resource, learners will be able to do the following (in the format 'behaviour, standard, and condition'):

- What level of clinical decision-making complexity is required?

## 4. Instructional strategy selection

- What instructional approach is most appropriate for your content:

  - Deductive approach (rules first, then examples)

  - Inductive approach (examples first, then rules)

  - Problem-based learning

  - Scenario-based learning (Cathy Moore methodology)

  - Storytelling approach

- What engagement strategy do you prefer:

  - Active learning (simulations, activities)

  - Collaborative learning (peer interaction)

  - Self-directed learning

  - Experiential learning

- How will you differentiate learning pathways for diverse learners?

## 5. Content complexity and structure

- What is the target duration for the complete learning experience?

- How much existing content is available versus needs creating from scratch? What kinds of materials do you have?

- Are there existing clinical vignettes or case studies to adapt?

- What level of interactivity is required (basic click-through, scenarios, simulations)?

# Scenario-based learning specifications

## 6. Scenario development requirements

- How many clinical scenarios are required to meet learning outcomes?

- What level of branching complexity is needed for each scenario (3-4 decision points or 5+ complex pathways)?

- Do scenarios require realistic consequence mapping and multiple outcome pathways?

- Are professional video scenarios with patient interactions required?

- What level of clinical authenticity is essential for scenario effectiveness?

## 7. Reflection and assessment integration

- How many reflection points should be embedded throughout the learning experience?

- What type of reflection activities are most appropriate:

  - Self-assessment tools

  - Peer reflection

  - Professional reflection journals

  - Case study analysis

- Will formative assessment be integrated throughout or summative at the end?

# Assessment and evaluation framework

## 8. Assessment sophistication requirements

- Will assessments be needed, and if so, what type?

- What level of assessment sophistication is required beyond basic multiple choice?

- Are adaptive questioning features required?

- Do you need scenario-based assessment questions?

- Is professional recognition or digital badge integration required?

- What documentation is required for assessment validation?

## 9. Evaluation methodology

- How will you measure learning effectiveness using Kirkpatrick's four levels?

- What performance analytics will you monitor post-launch?

- How frequently will content require updates based on evaluation data?

# Compliance and accessibility requirements

## 10. Regulatory compliance framework

- Are there specific regulatory or compliance requirements beyond WCAG 2.1 AA and PSBAR?

- What level of clinical accuracy validation is required?

- How many clinical review cycles should be planned (typically 2-3 for healthcare content)?

- What documentation trail is required for regulatory compliance?

- Are there specific professional body requirements that must be met?

## 11. Accessibility implementation

- How has accessibility been considered across all dimensions:

  - Colour contrast and visual design

  - Structural navigation and screen reader compatibility

  - Neurodiversity considerations

  - Individual pedagogic elements

  - Platform accessibility features

  - Navigation, access, and control mechanisms

- What assistive technologies must be supported?

- Are there specific accessibility testing requirements beyond standard WCAG compliance?

# Technical infrastructure and delivery

## 12. Platform selection and integration

- What LMS integration requirements exist?

- What are the technical constraints and preferences:

  - Blackboard Ultra (40-60 hours per finished hour)

  - Articulate Rise 360 (60-80 hours per finished hour)

  - Articulate Storyline 360 (120-180 hours per finished hour)

- What device compatibility is essential (desktop/mobile/tablet)?

- What is the expected learner volume and concurrent usage?

- Are there specific SCORM/xAPI compliance requirements?

## 13. Brand and media specifications

- Are there specific branding or visual identity requirements?

- What media production is required:

  - Professional video scenarios (budget £1,050 per scenario)

  - Audio narration and production

  - Custom graphics and animations

  - Interactive multimedia elements

- Are closed captions and audio transcripts required?

# Resource allocation and project management

## 14. Timeline and resource planning

- What are the critical project deadlines that cannot be moved?

- When must supplied materials be delivered to meet project milestones?

- What is the acceptable contingency buffer (recommend 20% for healthcare content)?

- Are there seasonal or operational constraints that affect the timeline?

## 15. Subject matter expert involvement

- How much SME time can be allocated to the project?

- For healthcare content, plan for 35-40% of total development time for SME involvement

- Who will be responsible for content accuracy validation?

- What is the process for managing multiple SME inputs and potential conflicts?

# Risk management and mitigation

## 16. Scope and complexity risks

- What are the potential scope expansion risks specific to your content area?

- Are there elements that might exceed initial complexity estimates?

- How will you manage the risk of additional compliance requirements emerging during development?

- What is the contingency plan if clinical accuracy requirements change?

## 17. Quality assurance framework

- What quality benchmarks must be met before launch?

- How will user acceptance testing be conducted?

- What is the process for handling post-launch content updates?

- How will you manage version control for regulatory compliance?

# Development approach and methodology

## 18. Content creation methodology

- Will you use a phased delivery approach for large projects?

- How will iterative review cycles be managed rather than single approval points?

- What is the preference for development methodology:

  - Agile development with regular sprints

  - Waterfall approach with sequential phases

  - Hybrid methodology combining both approaches

- How will you handle concurrent development and review processes?

## 19. Success measurement and continuous improvement

- What specific metrics will demonstrate project success?

- How will learning effectiveness be measured and validated?

- What feedback mechanisms will be implemented for continuous improvement?

- How will the project outcomes inform future eLearning development?

# Cost implications and budget framework

## 20. Budget allocation and cost factors

- Understanding the development time multipliers for your specifications:

  - Basic content: 113 hours per 60-minute course (£3,503)

  - Intermediate content: 534 hours per 60-minute course (£19,704 including media)

  - Advanced content: 750 hours per 60-minute course (£28,500 including media)

- What is the total available budget including contingency?

- Are there specific cost constraints that will influence design decisions?

- How will media production costs be managed within the overall budget?

Note: These questions incorporate evidence-based time allocation frameworks, compliance requirements, and pedagogical best practices. All time estimates are based on current research and should include appropriate contingency planning for healthcare content development.