## Start here
University of Southampton eLearning Cost Calculator | #VALUE!
About this tool
Tool purpose
This evidence-based calculator provides accurate time and cost estimates for eLearning development projects in healthcare and educational contexts. It incorporates peer-reviewed research and industry standards to support project planning and budget allocation decisions.
Scope
Suitable for: University of Southampton academic staff, external healthcare training providers, educational content developers
Content types: Healthcare training, educational modules, compliance training, scenario-based learning
Version information
Current Version: 2.1
Last Updated: 30 September 2025
Next Review: January 2026
Development history
v1.0 (2025) - Initial framework implementation
v2.0 (2025) - Added compliance multipliers, AI adjustments
v2.1 (2025) - Enhanced user interface, validation improvements
Primary research sources:
• Chapman Alliance (2010) - Industry benchmark study (n=249 organisations)
• ATD Research (2023) - Updated development time standards
• Tucker (2025) - AI-adjusted estimates and practitioner data
• University sector practice - Healthcare content specialisation
Compliance standards:
• WCAG 2.1 AA - Web Content Accessibility Guidelines
• PSBAR 2018 - Public Sector Bodies Accessibility Regulations
• EAA 2025 - European Accessibility Act
• Healthcare content validation requirements
Calculator features
Evidence-based multipliers:
• Platform-specific development ratios
• Complexity scaling factors (Basic 1.0x, Intermediate 1.5x, Advanced 2.0x)
• Healthcare SME involvement (35-40% of development time)
• Compliance overhead calculations (WCAG + PSBAR)
• Risk assessment and contingency planning
Quality assurance:
• Confidence ratings based on research evidence quality
• Input validation to prevent calculation errors
• Cross-sheet verification and error handling
How to use this calculator
Quick start:
1. Enter project details in 'Project_Input' sheet
2. Review cost breakdown in 'Cost_Breakdown' sheet
3. Assess project risks in 'Risk_Assessment' sheet
For detailed calculations, see 'Calculations' sheet
For reference data and multipliers, see 'Lookup_Tables' sheet
Support information
Tool developed by: Tamsyn Smith, Senior Learning Designer Team Lead, Digital Learning, iSolutions
University of Southampton
For questions or suggestions:
Email: T.M.Smith@soton.ac.uk
References
Chapman, B. (2010). How long does it take to create learning? Chapman Alliance LLC.
Defelice, R. (2023). Want to speed up training development time? TD Magazine, November 2023.
Tucker, C. (2025). Time estimates for elearning development. Retrieved from christytuckerlearning.com
Moore, C. (n.d.). Scenario based training example: Connect with Haji Kamal. Training Design.
Piskurich, G. M. (2015). Rapid instructional design: Learning ID fast and right (3rd ed.). Pfeiffer.
Research.com. (2025). eLearning trends: 2025 current data, analysis & insights.
Next sheet
→

## Project_Input
University of Southampton eLearning Cost Calculator |  |  | #VALUE!
Evidence-based pricing tool for healthcare and educational content
2025-11-28 |  |  | Version 2.2
Instructions: Complete all fields below. Green cells indicate valid inputs, red cells show conflicts.
Purpose: Input all project specifications here. Use dropdowns and validation indicators.
Project name: | Test project
Content duration (in minutes): | 60
Content type: | General academic |  | (Dropdown: Clinical/healthcare, General academic, Professional development
Percentage new content: | 75
Percentage existing content: | 25
Target audience: | UoS students |  | (Dropdown: UoS students, UoS staff/PGRs, External professionals)
Auto-selected platform: | Blackboard Ultra
Annual hosting cost (Course catalog only) | 0 |  | (This is expected to be a percentage of the revenue)
Choose authoring tool
Authoring tool: | MS Forms |  | (Note: Direct platform creation is not appropriate if you want to use scenarios)
Licence warning: | ✅ No additional license required
Scenario configuration
Number of scenarios: (0-20+, warning >20) | 1
Scenario complexity: (only if scenarios > 0) | Simple (1-2 decisions) | 🟢 Valid - scenarios and complexity selected | (Dropdown: Simple (1-2 decisions), Moderate (3-4 decisions), Complex (5-8 decisions))
Tool capabilities: | ✅ Simple only
Assessment and interaction
Assessment type: | Basic MCQ |  | (Dropdown: Basic MCQ, Comprehensive MCQ, Scenario-based, Adaptive)
Number of assessment questions: | 10
Reflection activities required: | 1
Interactive elements: | Minimal |  | (Dropdown: Minimal, Moderate, Extensive)
Immediate feedback required: | Yes |  | (Dropdown: Yes, No)
Certificate integration: | None |  | (Dropdown: None, Basic, Professional)
Compliance and accessibility
PSBAR applies to all UoS content. EAA applies to commercial courses sold to European customers. All options include WCAG 2.1 AA compliance as a baseline.
About EN 301 549 and EAA compliance:
The European Accessibility Act (EAA) uses EN 301 549 as the harmonised European standard for digital accessibility. EN 301 549 incorporates WCAG 2.1 Level AA as its foundation but extends beyond web content to cover additional ICT requirements including hardware, documentation, and specific software features. For e-learning resources, EAA compliance requires: - Accessibility statements for each learning resource (not just the platform) - Documentation of technical accessibility specifications and design processes - User feedback mechanisms for reporting accessibility issues - Validation processes for new content before deployment - Continuous monitoring and annual accessibility testing All UoS content must meet PSBAR compliance. Commercial courses sold to European customers must additionally meet EAA requirements.
Compliance level: | PSBAR + EAA compliance (includes WCAG 2.1 AA)
Additional compliance requirements: | None
Review cycles expected: | 2 |  | (Dropdown: 2, 3, 4, 5+)
Accessibility testing level: | Basic |  | (Dropdown: Basic, Comprehensive, Expert)
Media production
Video scenarios required: | No |  | (Dropdown: Yes, No)
Professional video production required: | No |  | (Dropdown: Yes, No)
If video required, production hours: | 0
Audio narration required: | No |  | (Dropdown: Yes, No)
Visual media required | None |  | (Dropdown:None, Custom graphics, Professional photography, Both graphics and photography)
Animation requirements: | None |  | (Dropdown: None, Basic, Advanced)
Staff rates
Learning Designer hourly rate | 30.79 |  | (Level 4, Point 35)
SME hourly rate | 40.19 |  | (Level 5, Point 44)
Source: Southampton pay scales with USS pension
Link: https://sotonac.sharepoint.com/teams/my_rewardrecognition/SitePages/Pay-Scales.aspx
Ongoing costs to consider
⚠️ Articulate license costs: | ✅ No license costs
⚠️ Platform hosting costs: | ✅ No hosting costs
⚠️ Content maintenance: | ⚠️ Budget for SME time and updates
⚠️ Accessibility updates: | ⚠️ May require updates for compliance changes
Note: These costs are NOT included in development calculation above
Next sheet
→

## Cost_Breakdown
University of Southampton eLearning Cost Calculator |  |  | #VALUE!
This breakdown shows detailed costs for your eLearning project, including development, media production, and SME requirements.
Project information
Project name: | Test project
Platform: | Blackboard Ultra
Authoring tool: | MS Forms
Complexity level: | Simple (1-2 decisions)
Content duration: | 60 minutes
Content type: | General academic
Compliance level: | PSBAR + EAA compliance (includes WCAG 2.1 AA)
TOTAL PROJECT COST: | £5,108.73
(Includes 20% contingency)
Cost per learning hour: | £5,108.73
Estimated timeline: | 2.8 weeks
SME time required: | 30 hours
Cost breakdown |  |  |  | Category | Amount
|  |  |  | Development | 3059.2944
|  |  |  | Media | 0
|  |  |  | SME | 1197.9835
|  |  |  | Contingency | 851.4556
Detailed cost breakdown
Development costs
Base development | 1231.6 | 24.11%
Scenario development | 215.53 | 4.219%
Assessment creation | 400.27 | 7.835%
Reflection activities | 369.48 | 7.232%
Certificate integration | 0 | 0%
Compliance overhead | 842.4144 | 16.49%
Development subtotal | 3059.2944 | 59.88%
Media production
Video scenarios | 0 | 0%
Custom graphics | 0 | 0%
Audio production | 0 | 0%
Animation | 0 | 0%
Professional photography | 0 | 0%
Media subtotal | 0 | 0%
Project management and SME
SME time (validation and review) | 1197.9835 | 23.45%
Project totals
Subtotal (before contingency) | 4257.2779 | 83.33%
Contingency (20%) | 851.4556 | 16.67%
TOTAL PROJECT COST | 5108.7335 | 100%
SME time requirements
Note: Clinical/healthcare content requires 35% SME time vs 30% for general content due to additional accuracy validation requirements.
Content validation: | 15 hours
Clinical accuracy review: | 9 hours
Feedback incorporation: | 6 hours
Total SME hours: | 30 hours
Total SME cost: | £1,197.98
Ongoing costs to consider
Annual platform hosting: | 0
Annual software licenses: | £0.00
Note: These costs are in addition to the development cost above
and should be budgeted annually for course maintenance.
What's included:
• Complete instructional design and content development
• All media production (graphics, audio, video as specified)
• All media production (graphics, audio, video as specified)
• Quality assurance testing
• SME review cycles and feedback incorporation
• 20% contingency for unforeseen requirements
What's not included:
• Annual accessibility testing and monitoring
• Annual review and updates to accessibility statements
• Annual platform hosting fees (shown separately)
• Ongoing software license costs (shown separately)
• Post-launch content updates or modifications
• Translation or localisation services
• Learning analytics implementation
Note: EAA compliance requires annual accessibility testing and continuous monitoring. Budget approximately 15-20% of original development hours annually for accessibility maintenance, statement updates, and validation of content changes.

## Risk_Assessment
University of Southampton eLearning Cost Calculator |  |  | #VALUE!
Purpose: Project risk evaluation and strategic recommendations based on inputs. Risk Scoring System: • Risk score 0-1: LOW (minimal mitigation required) • Risk score 2-3: MEDIUM (moderate oversight needed) • Risk score 4+: HIGH (intensive management required) The sheet provides automatic risk scoring with platform recommendations and mitigation strategies.
Test project
Risk assessment
Risk Level: | 🟢 LOW RISK
Risk Factor | Present | Weight | Score
High scenario count (>5) | No | 2 | 0
New content >80% | No | 1 | 0
Advanced complexity | No | 1 | 0
Multiple compliance | No | 1 | 0
Extensive media | No | 1 | 0
Complex assessment | No | 1 | 0
Risk mitigation recommendations:
LOW RISK: Standard project management approach suitable
Recommended actions:
Total risk score: | 0
Platform and authoring tool recommendations
Based on your specifications:
Selected platform: | Blackboard Ultra
Selected authoring tool: | MS Forms
Platform suitability: | ✓ Suitable for UoS students - free hosting
Authoring tool suitability: | ✓ No additional license costs
Recommendations: | ✅ Platform and tool well-matched for project requirements

## Calculations
University of Southampton eLearning Cost Calculator |  | #VALUE!
This sheet shows the detailed calculation breakdown for your project estimate.
Project overview
Project name: | Test project | 🟢 High confidence
Content duration (minutes): | 60 | 🟢 High confidence
Content type: | General academic | 🟢 High confidence
Platform: | Blackboard Ultra | 🟢 High confidence
Authoring tool: | MS Forms | 🟢 High confidence
Number of scenarios: | 1 | 🟢 High confidence
Scenario complexity: | Simple (1-2 decisions) | 🟢 High confidence
New content %: | 75 | 🟢 High confidence
Existing content %: | 25 | 🟢 High confidence
Compliance level | PSBAR + EAA compliance (includes WCAG 2.1 AA) | 🟢 High confidence
Development hours breakdown
Base development hours: | 40 | 🟢 High confidence
Scenario hours per scenario: | 7 | 🟡 Medium confidence
Scenario hours lookup check: | ✅ Valid lookup
Total scenario hours: | 7 | 🟢 High confidence
Assessment hours: | 13 | 🟢 High confidence
Reflection hours: | 12 | 🟢 High confidence
Certificate hours: | 0 | 🟢 High confidence
Compliance overhead hours (WCAG/PSBAR/EAA): | 27.36 | 🟡 Medium confidence
Total development hours: | 99.36 | 🟢 High confidence
Development costs
Base development cost: | 1231.6 | 🟢 High confidence
Scenario development cost: | 215.53 | 🟢 High confidence
Assessment creation cost: | 400.27 | 🟢 High confidence
Reflection activities cost: | 369.48 | 🟢 High confidence
Certificate integration cost: | 0 | 🟢 High confidence
Compliance overhead cost: | 842.4144 | 🟡 Medium confidence
Development subtotal: | 3059.2944 | 🟢 High confidence
Media production
Video scenarios cost: | 0 | 🟢 High confidence
Custom graphics cost: | 0 | 🟢 High confidence
Audio production cost: | 0 | 🟢 High confidence
Animation cost: | 0 | 🟢 High confidence
Photography cost: | 0 | 🟢 High confidence
Media subtotal: | 0 | 🟢 High confidence
SME requirements
SME time varies by content type:
SME percentage (35% clinical; 30% general): | 0.3 | 🟡 Medium confidence
SME hours required: | 29.808 | 🟢 High confidence
SME hourly rate: | 40.19 | 🟢 High confidence
Total SME cost: | 1197.9835 | 🟢 High confidence
Project totals
Development subtotal: | 3059.2944 | 🟢 High confidence
Media subtotal: | 0 | 🟢 High confidence
SME cost: | 1197.9835 | 🟢 High confidence
Project subtotal (before contingency): | 4257.2779 | 🟢 High confidence
Contingency (20%): | 851.4556 | 🟢 High confidence
TOTAL PROJECT COST: | 5108.7335 | 🟢 High confidence
Annual platform cost: | 0 | 🟢 High confidence
Annual license cost: | £0.00 | 🟢 High confidence
Validation and quality checks
Scenario validation: | ✅ Valid scenario configuration
Content percentages: | ✅ Valid: Total 100%
Platform suitability: | ✅ Platform matches audience
Budget assessment: | ✅ REASONABLE: Cost within normal range
Duration reasonableness: | ✅ Duration within normal range
Scenario count validation: | ✅ Valid | 🟢 High confidence
Compliance validation: | ✅ High confidence
EAA applicability check: | ✅ Compliance level appropriate for platform
Recommendations and guidance
Timeline estimate: | 2.8 weeks
Timeline guidance: | ✅ Timeline: 6-10 weeks typical
SME requirement guidance: | ✅ LOW: Manageable SME time required
Risk assessment: | 🟡 MEDIUM RISK: 20% contingency appropriate
Scenario guidance: | ✅ Good scenario count for focused learning
Recommended next steps: | 1. Proceed with detailed planning
Key considerations: | • Budget: £5,109 • Timeline: 2.8 weeks • SME time: 30 hours
Next sheet
→

## Lookup_Tables
University of Southampton eLearning Cost Calculator |  |  |  | #VALUE!
Purpose: Reference data for calculations. Do not modify unless updating framework standards.
Test project
Platform | Annual hosting cost | Target audience | Hours per finished hour | Column1 | Column2 | Column3 | Column4
Blackboard Ultra | 0 | UoS students | 40
Totara | 0 | UoS staff and PGRs | 40
Course Catalog | Variable (user input) | External professionals (CPD) | 40
Authoring tool | No scenarios | Simple (1-2 decisions) | Moderate (3-4 decisions) | Complex (5-8 decisions) | Max complexity | Annual licence costs | Evidence notes
Direct platform creation | 0 | 7 |  |  | Simple | 0 | Platform-native tools only. Adjusted from Chapman (2010) 45h baseline for 1-2 decision scenarios
MS Forms | 0 | 7 |  |  | Simple | 0 | Basic branching capability. Adjusted from Chapman (2010) for simplified scenarios and institutional efficiency
MS PowerPoint | 0 | 14 |  |  | Simple | 0 | Hyperlinked slides. Adjusted from Chapman (2010) 45h for 3-4 decisions to reflect 1-2 decisions in PowerPoint
Articulate Rise 360 | 0 | 25 | 35 |  | Moderate | £700+ | Professional rapid authoring. Based on Chapman (2010) Level 2 interactive content with institutional adjustments
ThingLink | 0 | 30 | 45 | 55 | Complex | 0 | Interactive media platform. Aligns with Chapman (2010) complex scenario benchmarks (45-55h)
Articulate Storyline 360 | 0 | 25 | 45 | 55 | Complex | £700+ | Advanced authoring with full customisation. Chapman (2010) Level 2-3 interactive content standards
Interactivity level | Minimal | Moderate | Extensive
Scenarios Included | 0 | 1-3 | 4+
Interactive Elements | Basic_clicks | Hotspots_tabs | Simulations
Assessment Type | Basic_MCQ | Comprehensive_MCQ | Scenario based
Video Production | No | 3_videos | 5+ professional
Reflection Activities | No | 3_components | Advanced tools
Assessment Type | Hours per question | Base hours
Basic MCQ | 0.5 | 10
Comprehensive MCQ | 0.8 | 15
Scenario-based | 1.2 | 25
Adaptive | 2 | 40
Compliance Type | Multiplier | Description
PSBAR compliance (includes WCAG 2.1 AA) | 0.35 | WCAG 2.1 AA baseline + PSBAR requirements
PSBAR + EAA compliance (includes WCAG 2.1 AA) | 0.4 | WCAG + PSBAR + EAA (commercial EU customers)
Clinical validation (reference only) | 0.25 | SME time adjustment used instead (35% vs 30%)
Compliance overhead breakdown:
WCAG 2.1 AA baseline: | 25-30% | Core accessibility standards
PSBAR additional: | 5-10% | UK public sector requirements
EAA additional (when applicable): | 5% | Resource statements + enhanced documentation
Combined PSBAR | 0.35 | WCAG baseline + PSBAR requirements
Combined PSBAR + EAA: | 0.4 | PSBAR (0.35) + EAA additional (0.05)
Accessibility testing adjustments
Testing Level | Adjustment factor
Basic | -0.02
Comprehensive | 0
Expert | 0.02
Media Type | Unit Cost | Description
Video scenario | 1050 | Per 3-minute scenario
Custom graphics | 500 | Per project
Audio production | 300 | Per hour of content
Professional photos | 200 | Per photoshoot
Advanced animation | 800 | Per project
Evidence-based multipliers: Platform hours (40-180 per finished hour). Compliance overhead: PSBAR 35%, PSBAR+EAA 40%. Media costs: £1050 per video scenario. Updated October 2025 based on EAA requirements.
IMPORTANT: Platform hours calculation
The "hours per finished hour" figures (40-150) represent
COMPLETE development time including ALL Chapman phases:
- Front-end analysis (9%)
Instructional design (13%)
- Storyboarding (11%)
- Graphic production (12%)
- Video production (6%)
- Audio production (6%)
- Authoring/programming (18%)
- QA testing (6%)
- Project management (6%)
- Project management (6%)
- Pilot testing (4%)
DO NOT add these phases separately to the calculation.
Items calculated SEPARATELY: compliance overhead,
assessment development, scenario development, media production.
Next sheet
→

## Maintenance_Guide
UoS eLearning Cost Calculator - Maintenance Guide
Item | Value
Last Updated | 2025-10-21
Version | 2.1
Purpose | Technical documentation for maintaining and updating the calculator
Calculator Architecture
Sheet Name | Purpose | Contains
Start here | User documentation | Instructions, references, version info
Project_Input | User data entry | All project parameters and selections
Cost_Breakdown | User-facing output | Formatted cost summary
Risk_Assessment | User-facing output | Risk analysis and contingency
Calculations | Backend calculations | All formulas and intermediate values
Lookup_Tables | Reference data | Platform rates, scenario hours, compliance multipliers
Maintenance_Guide | Technical documentation | This guide
Key Named Ranges - Input Parameters
Named Range | Cell Location | Description | Used In
Project_Duration | Project_Input B7 | Content duration in minutes | Calculations B18
Platform | Project_Input B12 | Auto-selected hosting platform | Calculations B18
Authoring_Tool | Project_Input B16 | Scenario authoring tool selection | Calculations B19
Number_Scenarios | Project_Input B20 | Count of scenarios | Calculations B19, B21
Scenario_Complexity | Project_Input B21 | Complexity level | Calculations B19
Key Named Ranges - Calculation Outputs
Named Range | Cell Location | Description | Formula Summary
Base_Development_Hours | Calculations B18 | Platform hosting hours | (Project_Duration/60) × VLOOKUP(Platform)
Scenario_Hours_Each | Calculations B19 | Hours per individual scenario | INDEX/MATCH on tbl_ScenarioHours
Total_Scenario_Hours | Calculations B21 | Total scenario development time | Number_Scenarios × B19
Total_Dev_Hours | Calculations B27 | Complete development time | Sum of all components
Excel Table: tbl_Platforms
Table Information
Location | Lookup_Tables A5:D8
Purpose | Platform hosting rates and properties
Referenced By | Calculations B18: VLOOKUP(Platform,tbl_Platforms,4,FALSE)
Column | Header | Data Type | Notes
A | Platform | Text | Blackboard Ultra, Totara, Course Catalog
B | Annual hosting cost | Text/Number | £0 or "Variable (user input)"
C | Target audience | Text | Maps to Project_Input B11
D | Hours per finished hour | Number | Currently all set to 40
Safe Modifications
✓ | Add new platforms by inserting rows within the table
✓ | Change hours per finished hour values in column D
✗ | Do NOT rename column headers without updating formulas
Excel Table: tbl_ScenarioHours
Table Information
Location | Lookup_Tables A10:H16
Purpose | Scenario development time by tool and complexity
Referenced By | Calculations B19: INDEX/MATCH on table
Column | Header | Data Type | Notes
A | Authoring tool | Text | Must match Project_Input B16 dropdown
B | No scenarios | Number | Always 0
C | Simple (1-2 decisions) | Number | Hours per scenario
D | Moderate (3-4 decisions) | Number or blank | Blank = not supported
E | Complex (5-8 decisions) | Number or blank | Blank = not supported
F | Max complexity | Text | Display only
G | Annual licence cost | Text | For user reference
H | Evidence notes | Text | Documents Chapman (2010) adjustments
Current Tool Rates (October 2025)
Tool | Simple | Moderate | Complex | Max Complexity
Direct platform creation | 7 | - | - | Simple
MS Forms | 7 | - | - | Simple
MS PowerPoint | 14 | - | - | Simple
Articulate Rise 360 | 25 | 35 | - | Moderate
ThingLink | 30 | 45 | 55 | Complex
Articulate Storyline 360 | 25 | 45 | 55 | Complex
Safe Modifications
✓ | Add new tools by inserting rows within the table
✓ | Change hour values
✓ | Leave cells BLANK for unsupported complexity (not "N/A" text)
✗ | Do NOT rename column headers without updating Calculations B19
✗ | Adding new complexity columns requires formula updates
Critical Formula: Calculations B18
Base Development Hours
40
Component | Description
Dependencies | Project_Duration, Platform, tbl_Platforms
What it does | Converts minutes to hours, multiplies by platform rate
If This Breaks - Check:
✓ | Platform value exists in tbl_Platforms column A
✓ | tbl_Platforms column D contains numbers
✓ | Named ranges point to correct cells
Critical Formula: Calculations B19
Scenario Hours Each
7
Component | Description
Dependencies | Number_Scenarios, Authoring_Tool, Scenario_Complexity, tbl_ScenarioHours
What it does | Returns 0 if no scenarios, otherwise looks up hours for tool/complexity combination. Returns 0 for unsupported combinations.
If This Breaks - Check:
✓ | Authoring_Tool value exists in tbl_ScenarioHours column A
✓ | Scenario_Complexity matches column header exactly
✓ | Blank cells (not "N/A" text) for unsupported combinations
✓ | Table name is still "tbl_ScenarioHours"
Common Maintenance Tasks
Adding a New Platform
Step | Action | Notes
1 | Click anywhere in tbl_Platforms | Lookup_Tables sheet
2 | Right-click last row → Insert → Table Row Below | Must use table row insertion
3 | Fill in all columns | Name, cost, audience, hours
4 | Update Project_Input B11 dropdown | Add new platform option
5 | Update Project_Input B12 formula if needed | Auto-selection logic
6 | Test | Verify Calculations B18 correct
No formula updates needed - table reference automatically includes new row
Adding a New Authoring Tool
Step | Action | Notes
1 | Click anywhere in tbl_ScenarioHours | Lookup_Tables sheet
2 | Right-click last row → Insert → Table Row Below | Must use table row insertion
3 | Fill in all columns | Leave BLANK for unsupported complexity
4 | Update Project_Input B16 dropdown | Add new tool option
5 | Update Project_Input B22 formula | Tool capabilities check
6 | Test with each complexity level | Verify validation works
No formula updates needed - table reference automatically includes new row
Changing Platform Hours
Step | Action | Notes
1 | Navigate to tbl_Platforms | Lookup_Tables sheet
2 | Change value in Column D | Hours per finished hour
3 | Test | Verify Calculations B18 updates
Document reason and evidence source in version notes
Changing Scenario Hours
Step | Action | Notes
1 | Navigate to tbl_ScenarioHours | Lookup_Tables sheet
2 | Change hour values in columns C-E | Simple/Moderate/Complex
3 | Update Evidence notes (Column H) | Explain change
4 | Test | Verify Calculations B19 updates
Leave cells BLANK for unsupported, do not use "N/A" text
Troubleshooting Guide
Problem | Likely Cause | Solution
#REF! error in Calculations | Named range pointing to deleted cell | Formulas → Name Manager → Check for #REF! → Delete or update
Validation showing error for valid combination | Text "N/A" in table instead of blank | Replace "N/A" text with blank cells in tbl_ScenarioHours
Base development hours showing #N/A | Platform name mismatch | Check exact match between Project_Input B12 and tbl_Platforms column A
Formulas stopped working after adding rows | Added rows outside table boundaries | Always insert rows WITHIN tables using table row insertion
Dropdown showing old values | Static list, not table reference | Update dropdowns to reference table columns dynamically
Testing Checklist
Test Category | Test Case | Expected Result
Basic Functionality
No scenarios | 60 min, 0 scenarios, Course Catalog | Base hours = 40
Simple scenario | 48 min, 1 simple PowerPoint | Base = 32, Scenario = 14
Platform change | Switch between platforms | Base hours update correctly
Multiple scenarios | 5 scenarios | Total = 5 × per-scenario hours
Validation
Invalid combo | PowerPoint + Moderate | Error shown, B19 = 0, B21 red
Valid simple | PowerPoint + Simple | Valid shown, B19 = 14
Valid moderate | Rise 360 + Moderate | Valid shown, B19 = 35
Valid complex | Storyline + Complex | Valid shown, B19 = 55
Edge Cases
Zero scenarios | Number_Scenarios = 0 | B20 shows "N/A - no scenarios"
Large numbers | 999 minutes, 50 scenarios | No errors, calculates correctly
All tools max | Each tool with maximum complexity | All show valid
Version Control Best Practices
Phase | Actions Required
Before Making Changes
1 | Save a dated backup copy of entire workbook
2 | Document the planned change in Start here sheet
3 | Test in a copy first before modifying live calculator
4 | Note which formulas reference the area you're changing
After Making Changes
1 | Test all affected formulas systematically
2 | Update version number in Start here sheet
3 | Update "Last Updated" date in Start here and this guide
4 | Document changes in development history
5 | Run full test suite (all test cases above)
Contact Information
Item | Details
Developer | Tamsyn Smith
Email | T.M.Smith@soton.ac.uk
Role | Senior Learning Designer Team Lead, Digital Learning, iSolutions
Institution | University of Southampton
Evidence Base Updates
When updating time estimates, ensure changes are documented with:
1 | Source citation (e.g., "Updated based on Chapman 2027 revised study")
2 | Rationale for institutional adjustments
3 | Comparison to previous values
4 | Review date for next evidence check
End of Maintenance Guide
Last reviewed: 21 October 2025
Next review: After major updates or annually